## Morn TVD
DAILY GEOLOGICAL REPORT
CONOCO PHILLIPS CANADA
WELL NAME |  |  |  | LOCATION |  |  |  | CONTRACTOR |  |  |  | RIG #
COPRC DODO CANYON E-76 |  |  |  | UNIT E-76 GRID 65-10 126-45 |  |  |  | BEAVER |  |  |  | 2
DATE |  | REPORT |  | REPORTING TO |  |  | WELLSITE GEOLOGIST |  |  | CELL PHONE |  | RIG PHONE
2013-12-27 |  | 2 |  | Dave Oakley |  |  | Gerry Pasveer |  |  | 403-998-2850 |  | 403-538-6808
KB (m) |  | GL (m) |  | SPUD DATE |  | DAY No. |  | FORMATION |  |  | WEATHER CONDITIONS
273.4 |  | 268.2 |  | 2013-12-28 06:30 |  | 6 |  | surface |  |  | -48 C, with wind chill
|  |  |  | 06:00 STATUS: |  |  | Pre Spud safety meeting
0600 DEPTH |  | LAST REPORT |  | PROGRESS |  | BIT # | Bit Type |  | BIT SIZE |  | TOTAL MTRS |  | Bit Hrs
20 |  | 0 |  | 20 |  | 1 | REED |  | 311mm |  | 20
DRILLING FLUID |  |  | DEN (kg/m^3) |  | VISCOSITY |  | WATER LOSS |  | pH | DAILY DRLG HRS |  | ROP (m/hr)
Floc |  |  | 1000 |  | 33 | [6 empty] | -
OPERATIONS SUMMARY - PAST 24 HOURS
Rig Service; Rig in smart anti collision system with system hand; Finish rigging up Top Drive, recalibrate all functions; Pick up and Steam 9" drill collers and 311mm tooth bit; Pick up and Steam BHA, circulate check for leaks; Extend hydraulic hose for Top Drive; Pre Spud Safety meeting and Hazard Hunt; Spud well 06:30hrs, Drill from 0m to 20m; Crew Change, Safety meeting and Prespud with second crew.
OPERATIONS FORECAST - NEXT 24 HOURS
Complete Spud meeting with second crew, begin drilling 311mm surface hole.
BACKGROUND TOTAL GAS (Units, 100 Units = 1%) | [6 empty] | GAS SHOWS (Units, 100 Units = 1%)
From | To | ROP | Max | Avg | Gross Lith. |  | From | To | Max | Prev. | Lithology
FORMATION / MARKER TOPS
FORMATION |  | PROGNOSIS |  | SAMPLE |  |  | FORMATION |  | PROGNOSIS |  | SAMPLE
MARKER TOPS |  | TVD | SS | MD | TVD | SS | MARKER TOPS |  | TVD | SS | MD | TVD | SS
Little Bear |  | 30.4 | 243
Slater River |  | 76.4 | 197
Arctic red |  | 827.4 | -554
Martin House |  | 933.4 | -660
Imperial |  | 968.4 | -695
KOP (5°/30m) |  | 1481.7 | -1208.3
KOP (7°/30m) |  | 1625.8985 | -1352.4985
Upper Canol |  | 1653.4 | -1380
** Lower Canol |  | 1686.4 | -1413
Target Zone Heel |  | 1774.4 | -1501
Toe (E-76)rev2.0 |  | 1804.4 | -1531
COMMENTS
** Primary Target
Secondary Target