## Morn TVD
DAILY GEOLOGICAL REPORT
CONOCO PHILLIPS CANADA
WELL NAME |  |  |  | LOCATION |  |  |  | CONTRACTOR |  |  |  | RIG #
COPRC DODO CANYON E-76 |  |  |  | UNIT E-76 GRID 65-10 126-45 |  |  |  | BEAVER |  |  |  | 2
DATE |  | REPORT |  | REPORTING TO |  |  | WELLSITE GEOLOGIST |  |  | CELL PHONE |  | RIG PHONE
2014-01-04 |  | 9 |  | Dave Oakley |  |  | Dave Lawrence |  |  | 403-803-9201 |  | 403-538-6808
KB (m) |  | GL (m) |  | SPUD DATE |  | DAY No. |  | FORMATION |  |  | WEATHER CONDITIONS
273.4 |  | 268.2 |  | 2013-12-28 06:30 |  | 13 |  | Slater River |  |  | -39 C, with wind chill
|  |  |  | 06:00 STATUS: |  |  | Cement Surface Casing
0600 DEPTH |  | LAST REPORT |  | PROGRESS |  | BIT # | Bit Type |  | BIT SIZE |  | TOTAL MTRS |  | Bit Hrs
603 |  | 592 |  | 11 |  | 1 | REED |  | 311mm |  | 603 |  | 41
DRILLING FLUID |  |  | DEN (kg/m^3) |  | VISCOSITY |  | WATER LOSS |  | pH | DAILY DRLG HRS |  | ROP (m/hr)
Gel Chem |  |  | 1200 |  | 95 |  | 11 |  | 8 | 1.75 |  | 6
OPERATIONS SUMMARY - PAST 24 HOURS
Ream to bottom, drill ahead from 592-603m, circ & cond mud, POOH, lay down drill collars & BHA, rig to & run 244.5mm surface casing, circ & cond mud, rig up cementers and prepare to cement casing.
OPERATIONS FORECAST - NEXT 24 HOURS
Finish cementing, rig out cementers, nipple up and pressure test.
BACKGROUND TOTAL GAS (Units, 100 Units = 1%) | [6 empty] | GAS SHOWS (Units, 100 Units = 1%)
From | To | ROP | Max | Avg | Gross Lith. |  | From | To | Max | Prev. | Lithology
592 | 603 | 6 | 100 | 70 | Shale
FORMATION / MARKER TOPS
FORMATION |  | PROGNOSIS |  | SAMPLE |  |  | FORMATION |  | PROGNOSIS |  | SAMPLE
MARKER TOPS |  | TVD | SS | MD | TVD | SS | MARKER TOPS |  | TVD | SS | MD | TVD | SS
Little Bear |  | 30.4 | 243 | 31 | 31 | 242.4
Slater River |  | 76.4 | 197 | 76 | 76 | 197.4
Arctic red |  | 827.4 | -554
Martin House |  | 933.4 | -660
Imperial |  | 968.4 | -695
KOP (5°/30m) |  | 1481.7 | -1208.3
KOP (7°/30m) |  | 1625.8985 | -1352.4985
Upper Canol |  | 1653.4 | -1380
** Lower Canol |  | 1686.4 | -1413
Target Zone Heel |  | 1774.4 | -1501
Toe (E-76)rev2.0 |  | 1804.4 | -1531
COMMENTS
** Primary Target
Secondary Target