## Morn TVD
DAILY GEOLOGICAL REPORT
CONOCO PHILLIPS CANADA
WELL NAME |  |  |  | LOCATION |  |  |  | CONTRACTOR |  |  |  | RIG #
COPRC DODO CANYON E-76 |  |  |  | UNIT E-76 GRID 65-10 126-45 |  |  |  | BEAVER |  |  |  | 2
DATE |  | REPORT |  | REPORTING TO |  |  | WELLSITE GEOLOGIST |  |  | CELL PHONE |  | RIG PHONE
2014-01-07 |  | 11 |  | Dave Oakley |  |  | Dave Lawrence |  |  | 403-803-9201 |  | 403-538-6808
KB (m) |  | GL (m) |  | SPUD DATE |  | DAY No. |  | FORMATION |  |  | WEATHER CONDITIONS
273.4 |  | 268.2 |  | 2013-12-28 06:30 |  | 16 |  | Slater River |  |  | -30 C, with wind chill
|  |  |  | 06:00 STATUS: |  |  | Drilling 222mm hole
0600 DEPTH |  | LAST REPORT |  | PROGRESS |  | BIT # | Bit Type |  | BIT SIZE |  | TOTAL MTRS |  | Bit Hrs
808 |  | 603 |  | 205 |  | 2 | ULTERA 616 |  | 222 |  | 205 |  | 8.25
DRILLING FLUID |  |  | DEN (kg/m^3) |  | VISCOSITY |  | WATER LOSS |  | pH | DAILY DRLG HRS |  | ROP (m/hr)
Invert |  |  | 950 |  | 50 |  |  |  |  | 8.25 |  | 25
OPERATIONS SUMMARY - PAST 24 HOURS
Rig serice; Review Top Drive trouble shooting with Top Drive Hand; Pick up Drill pipe; RIH; Tag Cement @ 586m; Displace 27 m3 of H2O to Invert; BOP Drill, well secure in 90 secs; Drill out Cement, Float and Shoe @ 603m; Drill 222mm hole from 603m to 761m; Change out Liners in Pump #1 from 5 1/2" to 5" liners; ( 24:00hrs) Change out Liners in Pump #1 from 5 1/2" to 5" liners; Change Module Seal in Pump #2; Drill 222mm hole from 761m to
OPERATIONS FORECAST - NEXT 24 HOURS
Drill ahead on Intermediate section
BACKGROUND TOTAL GAS (Units, 100 Units = 1%) | [6 empty] | GAS SHOWS (Units, 100 Units = 1%)
From | To | ROP | Max | Avg | Gross Lith. |  | From | To | Max | Prev. | Lithology
603 | 780 | 25 | 140 | 80 | Shale
FORMATION / MARKER TOPS
FORMATION |  | PROGNOSIS |  | SAMPLE |  |  | FORMATION |  | PROGNOSIS |  | SAMPLE
MARKER TOPS |  | TVD | SS | MD | TVD | SS | MARKER TOPS |  | TVD | SS | MD | TVD | SS
Little Bear |  | 30.4 | 243 | 31 | 31 | 242.4
Slater River |  | 76.4 | 197 | 76 | 76 | 197.4
Arctic red |  | 827.4 | -554
Martin House |  | 933.4 | -660
Imperial |  | 968.4 | -695
KOP (5°/30m) |  | 1481.7 | -1208.3
KOP (7°/30m) |  | 1625.8985 | -1352.4985
Upper Canol |  | 1653.4 | -1380
** Lower Canol |  | 1686.4 | -1413
Target Zone Heel |  | 1774.4 | -1501
Toe (E-76)rev2.0 |  | 1804.4 | -1531
COMMENTS
Night Geo: Gerry Pasveer (403-998-2850)
** Primary Target
Secondary Target