## Morn TVD
DAILY GEOLOGICAL REPORT
CONOCO PHILLIPS CANADA
WELL NAME |  |  |  | LOCATION |  |  |  | CONTRACTOR |  |  |  | RIG #
COPRC DODO CANYON E-76 |  |  |  | UNIT E-76 GRID 65-10 126-45 |  |  |  | BEAVER |  |  |  | 2
DATE |  | REPORT |  | REPORTING TO |  |  | WELLSITE GEOLOGIST |  |  | CELL PHONE |  | RIG PHONE
2014-01-08 |  | 12 |  | Dave Oakley |  |  | Dave Lawrence |  |  | 403-803-9201 |  | 403-538-6808
KB (m) |  | GL (m) |  | SPUD DATE |  | DAY No. |  | FORMATION |  |  | WEATHER CONDITIONS
273.4 |  | 268.2 |  | 2013-12-28 06:30 |  | 17 |  | Imperial Fm |  |  | -30 C, with wind chill
|  |  |  | 06:00 STATUS: |  |  | Drilling 222mm hole
0600 DEPTH |  | LAST REPORT |  | PROGRESS |  | BIT # | Bit Type |  | BIT SIZE |  | TOTAL MTRS |  | Bit Hrs
1293 |  | 808 |  | 485 |  | 2 | ULTERA 616 |  | 222 |  | 690 |  | 29.25
DRILLING FLUID |  |  | DEN (kg/m^3) |  | VISCOSITY |  | WATER LOSS |  | pH | DAILY DRLG HRS |  | ROP (m/hr)
Invert |  |  | 940 |  | 48 |  |  |  |  | 18.5 |  | 25
OPERATIONS SUMMARY - PAST 24 HOURS
Drill 222m hole from from 808m to 989m; Perform Formation integrity test, Hold Pressure at 2500 kPa for 10 mins; Drill from 989m to 1179m ( 24:00 ); Drill from 1179m to 1293m
OPERATIONS FORECAST - NEXT 24 HOURS
Drill ahead on Intermediate section
BACKGROUND TOTAL GAS (Units, 100 Units = 1%) | [6 empty] | GAS SHOWS (Units, 100 Units = 1%)
From | To | ROP | Max | Avg | Gross Lith. |  | From | To | Max | Prev. | Lithology
780 | 1280 | 25 | 155 | 70 | Shale
FORMATION / MARKER TOPS
FORMATION |  | PROGNOSIS |  | SAMPLE |  |  | FORMATION |  | PROGNOSIS |  | SAMPLE
MARKER TOPS |  | TVD | SS | MD | TVD | SS | MARKER TOPS |  | TVD | SS | MD | TVD | SS
Little Bear |  | 30.4 | 243 | 31 | 31 | 242.4
Slater River |  | 76.4 | 197 | 76 | 76 | 197.4
Arctic red |  | 827.4 | -554 | 800.5 | 800.46 | -527.06
Martin House |  | 933.4 | -660 | 938.5 | 938.44 | -665.04
Imperial |  | 968.4 | -695 | 975.5 | 975.43 | -702.03
KOP (5°/30m) |  | 1481.7 | -1208.3
KOP (7°/30m) |  | 1630.45 | -1356.6
Upper Canol |  | 1653.4 | -1380
** Lower Canol |  | 1686.4 | -1413
Target Zone Heel |  | 1774.4 | -1501
Toe (E-76)rev2.0 |  | 1804.4 | -1531
COMMENTS
Night Geo: Gerry Pasveer (403-998-2850)
** Primary Target
Secondary Target