## Morn TVD
DAILY GEOLOGICAL REPORT
CONOCO PHILLIPS CANADA
WELL NAME |  |  |  | LOCATION |  |  |  | CONTRACTOR |  |  |  | RIG #
COPRC DODO CANYON E-76 |  |  |  | UNIT E-76 GRID 65-10 126-45 |  |  |  | BEAVER |  |  |  | 2
DATE |  | REPORT |  | REPORTING TO |  |  | WELLSITE GEOLOGIST |  |  | CELL PHONE |  | RIG PHONE
2014-01-10 |  | 14 |  | Dave Oakley |  |  | Dave Lawrence |  |  | 403-803-9201 |  | 403-538-6808
KB (m) |  | GL (m) |  | SPUD DATE |  | DAY No. |  | FORMATION |  |  | WEATHER CONDITIONS
273.4 |  | 268.2 |  | 2013-12-28 06:30 |  | 19 |  | Imperial Fm |  |  | -30 C, with wind chill
|  |  |  | 06:00 STATUS: |  |  | Tripping in hole with new Bit and Motor.
0600 DEPTH |  | LAST REPORT |  | PROGRESS |  | BIT # | Bit Type |  | BIT SIZE |  | TOTAL MTRS |  | Bit Hrs
1599 |  | 1556 |  | 43 |  | 3 | ULTERA 616 |  | 222 |  | 996 |  | 50.75
DRILLING FLUID |  |  | DEN (kg/m^3) |  | VISCOSITY |  | WATER LOSS |  | pH | DAILY DRLG HRS |  | ROP (m/hr)
Invert |  |  | 1000 |  | 55 |  |  |  |  | 6.5 |  | 5.2
OPERATIONS SUMMARY - PAST 24 HOURS
Drill 222mm Build Section from 1556m to 1578m; FT Pipe Rams, 8 secs open - closed; FT Flare Igniter; Change Oil in Pump #1; Drill from 1578m to 1599m; circ Bottoms up; Perform Formation Integrety test, Hold 4500 kPa for 10 mins; Trip out of hole to change Bit, POOH at 60m; ( 24:00 hrs ); POOH, Make and Pick up new Bit and Mud Motor; Trip in hole.
OPERATIONS FORECAST - NEXT 24 HOURS
Trip in Hole with Bit #4 Smith FHI18B 222mm Tri Cone Bit; Drill ahead on Intermediate Build Section
BACKGROUND TOTAL GAS (Units, 100 Units = 1%) | [6 empty] | GAS SHOWS (Units, 100 Units = 1%)
From | To | ROP | Max | Avg | Gross Lith. |  | From | To | Max | Prev. | Lithology
1560 | 1599 | 7 | 70 | 50 | Shale
FORMATION / MARKER TOPS
FORMATION |  | PROGNOSIS |  | SAMPLE |  |  | FORMATION |  | PROGNOSIS |  | SAMPLE
MARKER TOPS |  | TVD | SS | MD | TVD | SS | MARKER TOPS |  | TVD | SS | MD | TVD | SS
Little Bear |  | 30.4 | 243 | 31 | 31 | 242.4
Slater River |  | 76.4 | 197 | 76 | 76 | 197.4
Arctic red |  | 827.4 | -554 | 800.5 | 800.46 | -527.06
Martin House |  | 933.4 | -660 | 938.5 | 938.44 | -665.04
Imperial |  | 968.4 | -695 | 975.5 | 975.43 | -702.03
KOP (5°/30m) |  | 1481.7 | -1208.3 | 1466 | 1452.2408 | -1178.8408
KOP (7°/30m) |  | 1625.8985 | -1352.4985
Upper Canol |  | 1653.4 | -1380
** Lower Canol |  | 1694.4 | -1421
Target Zone Heel |  | 1774.4 | -1501
Toe (E-76)rev2.0 |  | 1804.4 | -1531
COMMENTS
Night Geo: Gerry Pasveer (403-998-2850)
** Primary Target
Secondary Target