## Morn TVD
DAILY GEOLOGICAL REPORT
CONOCO PHILLIPS CANADA
WELL NAME |  |  |  | LOCATION |  |  |  | CONTRACTOR |  |  |  | RIG #
COPRC DODO CANYON E-76 |  |  |  | UNIT E-76 GRID 65-10 126-45 |  |  |  | BEAVER |  |  |  | 2
DATE |  | REPORT |  | REPORTING TO |  |  | WELLSITE GEOLOGIST |  |  | CELL PHONE |  | RIG PHONE
2014-01-12 |  | 16 |  | Dave Oakley |  |  | Dave Lawrence |  |  | 403-803-9201 |  | 403-538-6808
KB (m) |  | GL (m) |  | SPUD DATE |  | DAY No. |  | FORMATION |  |  | WEATHER CONDITIONS
273.4 |  | 268.2 |  | 2013-12-28 06:30 |  | 21 |  | Lower Canol |  |  | -35 C, with wind chill
|  |  |  | 06:00 STATUS: |  |  | Drill 222mm Build Section
0600 DEPTH |  | LAST REPORT |  | PROGRESS |  | BIT # | Bit Type |  | BIT SIZE |  | TOTAL MTRS |  | Bit Hrs
1751 |  | 1702 |  | 49 |  | 4 | Smith |  | 222 |  | 114 |  | 25.5
DRILLING FLUID |  |  | DEN (kg/m^3) |  | VISCOSITY |  | WATER LOSS |  | pH | DAILY DRLG HRS |  | ROP (m/hr)
Invert |  |  | 1010 |  | 56 |  |  |  |  | 11 |  | 4.5
OPERATIONS SUMMARY - PAST 24 HOURS
Trip out of Hole; Change Motor from 1.83 degrees to 2.12 degrees bend; Inspect Bit; OK; Trip in hole; Drill 222mm Build section from 1702 to 1726m ( 24:00hrs ); Drill to 1731m; Rig Service, FT Pipe Rams, closed 3 secs; Drill from 1731m to 1751m
OPERATIONS FORECAST - NEXT 24 HOURS
Drill ahead on 222mm Build Section
BACKGROUND TOTAL GAS (Units, 100 Units = 1%) | [6 empty] | GAS SHOWS (Units, 100 Units = 1%)
From | To | ROP | Max | Avg | Gross Lith. |  | From | To | Max | Prev. | Lithology
1702 | 1712 | 5 | 300 | 100 | Shale
1712 | 1740 | 5 | 500 | 375 | Shale
FORMATION / MARKER TOPS
FORMATION |  | PROGNOSIS |  | SAMPLE |  |  | FORMATION |  | PROGNOSIS |  | SAMPLE
MARKER TOPS |  | TVD | SS | MD | TVD | SS | MARKER TOPS |  | TVD | SS | MD | TVD | SS
Little Bear |  | 30.4 | 243 | 31 | 31 | 242.4
Slater River |  | 76.4 | 197 | 76 | 76 | 197.4
Arctic red |  | 827.4 | -554 | 791 | 791 | -517.6
Martin House |  | 933.4 | -660 | 929 | 928.9386 | -655.5386
Imperial |  | 968.4 | -695 | 966.3 | 966.2325 | -692.8325
KOP (5°/30m) |  | 1481.7 | -1208.3 | 1455 | 1454.6647 | -1181.2647
KOP (7°/30m) |  | 1625.8985 | -1352.4985 | 1630 | 1625.9 | -1352.5
Upper Canol |  | 1653.4 | -1380 | 1665 | 1657.3821 | -1383.9821
** Lower Canol |  | 1686 | -1413 | 1700.5 | 1687.9 | -1414.4
Target Zone Heel |  | 1774.4 | -1501
Toe (E-76)rev2.0 |  | 1804.4 | -1531
COMMENTS
Night Geo: Gerry Pasveer (403-998-2850)
** Primary Target
Secondary Target