## Morn TVD
DAILY GEOLOGICAL REPORT
CONOCO PHILLIPS CANADA
WELL NAME |  |  |  | LOCATION |  |  |  | CONTRACTOR |  |  |  | RIG #
COPRC DODO CANYON E-76 |  |  |  | UNIT E-76 GRID 65-10 126-45 |  |  |  | BEAVER |  |  |  | 2
DATE |  | REPORT |  | REPORTING TO |  |  | WELLSITE GEOLOGIST |  |  | CELL PHONE |  | RIG PHONE
2014-01-15 |  | 19 |  | Dave Oakley |  |  | Dave Lawrence |  |  | 403-803-9201 |  | 403-538-6808
KB (m) |  | GL (m) |  | SPUD DATE |  | DAY No. |  | FORMATION |  |  | WEATHER CONDITIONS
273.4 |  | 268.2 |  | 2013-12-28 06:30 |  | 24 |  | Lower Canol |  |  | -35 C, with wind chill
|  |  |  | 06:00 STATUS: |  |  | Running 7" Casing…
0600 DEPTH |  | LAST REPORT |  | PROGRESS |  | BIT # | Bit Type |  | BIT SIZE |  | TOTAL MTRS |  | Bit Hrs
1908 |  | 1908
DRILLING FLUID |  |  | DEN (kg/m^3) |  | VISCOSITY |  | WATER LOSS |  | pH | DAILY DRLG HRS |  | ROP (m/hr)
Invert |  |  | 1025 |  | 75
OPERATIONS SUMMARY - PAST 24 HOURS
POOH; Lay down Directional tools and Bit; ull wear bushing; Safety meeting with Schlumberger Wireline Loggers; Rig to and Log well ( good hole conditions; 1819.10m); Rig out Wireline; Slip and Cut 25m off Drill Line; Change out Mud savor valve on Top Drive; ( 24:00hrs ); Change out Mud Savor valve; Safety meeting with Tong hand from Hallmark Tong Service; Run 7" Casing.
OPERATIONS FORECAST - NEXT 24 HOURS
Run Casing; Cement; Change BOP; Pressure Test.
BACKGROUND TOTAL GAS (Units, 100 Units = 1%) | [6 empty] | GAS SHOWS (Units, 100 Units = 1%)
From | To | ROP | Max | Avg | Gross Lith. |  | From | To | Max | Prev. | Lithology
FORMATION / MARKER TOPS
FORMATION |  | PROGNOSIS |  | SAMPLE |  |  | FORMATION |  | PROGNOSIS |  | WIRELINE
MARKER TOPS |  | TVD | SS | MD | TVD | SS | MARKER TOPS |  | TVD | SS | MD | TVD | SS
Little Bear |  | 30.4 | 243 | 31 | 31 | 242.4 |  |  |  |  | 24.8002 | 24.8 | 248.6
Slater River |  | 76.4 | 197 | 76 | 76 | 197.4 |  |  |  |  | 65 | 65 | 208.4
Arctic red |  | 827.4 | -554 | 791 | 791 | -517.6 |  |  |  |  | 788.0357 | 788 | -514.6
Martin House |  | 933.4 | -660 | 929 | 928.9386 | -655.5386 |  |  |  |  | 926.7609 | 926.7 | -653.3
Imperial |  | 968.4 | -695 | 966.3 | 966.2325 | -692.8325 |  |  |  |  | 963.467 | 963.4 | -690
KOP (5°/30m) |  | 1481.7 | -1208.3 | 1455 | 1454.6647 | -1181.2647
KOP (7°/30m) |  | 1625.8985 | -1352.4985 | 1630 | 1625.9 | -1352.5
Upper Canol |  | 1653.4 | -1380 | 1665 | 1657.3821 | -1383.9821 |  |  |  |  | 1663.2357 | 1655.8 | -1382.4
** Lower Canol |  | 1686.4 | -1413 | 1700.7234 | 1687.9 | -1414.5 |  |  |  |  | 1698.7759 | 1686.3 | -1412.9
Target Zone Heel |  | 1777 | -1503.6 | 1908 | 1776.82 | -1503.42
Toe (E-76)rev2.0 |  | 1804.4 | -1531
COMMENTS
Night Geo: Gerry Pasveer (403-998-2850) Loggers Total Depth: 1819.1 mMD ( 1761.51mTVD, -1488.11mSS, 138.64mVS) @ 67.15 degrees Inclination 70.08m North 119.63m West of Well Center
** Primary Target
Secondary Target