## Morn TVD
DAILY GEOLOGICAL REPORT
CONOCO PHILLIPS CANADA
WELL NAME |  |  |  | LOCATION |  |  |  | CONTRACTOR |  |  |  | RIG #
COPRC DODO CANYON E-76 |  |  |  | UNIT E-76 GRID 65-10 126-45 |  |  |  | BEAVER |  |  |  | 2
DATE |  | REPORT |  | REPORTING TO |  |  | WELLSITE GEOLOGIST |  |  | CELL PHONE |  | RIG PHONE
2014-01-17 |  | 21 |  | Dave Oakley |  |  | Dave Lawrence |  |  | 403-803-9201 |  | 403-538-6808
KB (m) |  | GL (m) |  | SPUD DATE |  | DAY No. |  | FORMATION |  |  | WEATHER CONDITIONS
273.4 |  | 268.2 |  | 2013-12-28 06:30 |  | 26 |  | Lower Canol |  |  | -30 C, with wind chill
|  |  |  | 06:00 STATUS: |  |  | Drilling 156mm lateral section.
0600 DEPTH |  | LAST REPORT |  | PROGRESS |  | BIT # | Bit Type |  | BIT SIZE |  | TOTAL MTRS |  | Bit Hrs
1945 |  | 1908 |  | 37 |  | 4 | Smith 613 |  | 156 |  | 37 |  | 4
DRILLING FLUID |  |  | DEN (kg/m^3) |  | VISCOSITY |  | WATER LOSS |  | pH | DAILY DRLG HRS |  | ROP (m/hr)
Invert |  |  | 1080 |  | 75 |  |  |  |  | 4 |  | 9.25
OPERATIONS SUMMARY - PAST 24 HOURS
Nipple down BOP; Remove Catch Can; Prepare Mandrel Hanger; Unable to get seal; Set BOP Back Down; Nipple up; Make and Pickup Directional tools and Bit; ( Smith MSI 613_156mm, Motor Vbend 1.36 degrees; 1.66m Bit to Bend; RIH 2 joints, Pressure Test; low 1400 kPa 10 mins; high 20,000 kPa 10 mins, Held Good; Trip in Hole, Tag Cement at 1893m; Drill out Cement ( 24:00hrs );Drill out Float (1895m) and Shoe @ 1907m, Drill to 1914m; Circulate Bottoms up; Perform Formation Integrity test; Drill 156mm Lateral section from 1914m to 1945
OPERATIONS FORECAST - NEXT 24 HOURS
Drill ahead on 156mm lateral section….
BACKGROUND TOTAL GAS (Units, 100 Units = 1%) | [6 empty] | GAS SHOWS (Units, 100 Units = 1%)
From | To | ROP | Max | Avg | Gross Lith. |  | From | To | Max | Prev. | Lithology
1908 | 1935 | 9 | 1000 | 400 | SHALE
FORMATION / MARKER TOPS
FORMATION |  | PROGNOSIS |  | SAMPLE |  |  | FORMATION |  | PROGNOSIS |  | WIRELINE
MARKER TOPS |  | TVD | SS | MD | TVD | SS | MARKER TOPS |  | TVD | SS | MD | TVD | SS
Little Bear |  | 30.4 | 243 | 31 | 31 | 242.4 |  |  |  |  | 24.8002 | 24.8 | 248.6
Slater River |  | 76.4 | 197 | 76 | 76 | 197.4 |  |  |  |  | 65 | 65 | 208.4
Arctic red |  | 827.4 | -554 | 791 | 791 | -517.6 |  |  |  |  | 788.0357 | 788 | -514.6
Martin House |  | 933.4 | -660 | 929 | 928.9386 | -655.5386 |  |  |  |  | 926.7609 | 926.7 | -653.3
Imperial |  | 968.4 | -695 | 966.3 | 966.2325 | -692.8325 |  |  |  |  | 963.467 | 963.4 | -690
KOP (5°/30m) |  | 1481.7 | -1208.3 | 1455 | 1454.6647 | -1181.2647
KOP (7°/30m) |  | 1625.8985 | -1352.4985 | 1630 | 1625.9 | -1352.5
Upper Canol |  | 1653.4 | -1380 | 1665 | 1657.3821 | -1383.9821 |  |  |  |  | 1663.2357 | 1655.8 | -1382.4
** Lower Canol |  | 1686.4 | -1413 | 1700.7234 | 1687.9 | -1414.5 |  |  |  |  | 1698.7759 | 1686.3 | -1412.9
Target Zone Heel |  | 1777 | -1503.6 | 1908 | 1776.82 | -1503.42
Toe (E-76)rev2.0 |  | 1804.4 | -1531
COMMENTS
Night Geo: Gerry Pasveer (403-998-2850) DIRECTIONAL: In @ 1908m Projected vertical section azimuth. 299.99° Motor Bend: 1.36° Magnetic Declination 22.996° Survey tool offset: 19.50m Gamma offset: 13.93m
** Primary Target
Secondary Target