## DR-03
DR-03 | RC 2.1.29.7 | 15 | [11 empty] | 2014-03-02 | 7568 | Vendor | Field Ticket | Account Description | Account | Amount | Comment | Brian Dickson
[12 empty] | OPERATION DATE: | 2016-09-26 |  |  | JAZA Oilfield Consulting Ltd. | APA-389 | Contract Supervision | 70021 | 1287 | Supervision for Sept. 25 & 26
[12 empty] | REPORT DATE: | 2016-09-27 |  |  | Qwest Helicopters | 41670 | Air Transportation | 70002 | 800 | Helicopter to fly to location
|  | CANADA LTD. | [9 empty] | REPORT No.: |  | 3
| WELL NAME: |  | APACHE AMOCO A-4 POINTED MOUNTAIN A-55 |  |  |  |  | License # |  | N911 |  | PAGE No: | 1 | of | 1
| UWI: |  | 300/A-55-6030-12345/02 |  |  |  |  | Surface Loc: | A-55-6030-12345 |  |  | AFE No.: | 20-14-0478 | ACL WI: | 100%
| ELEVATIONS: |  | KB: | 455.6 | m | GL: | 450.7 | m | KB-THF: | 6.4 | m | AFE Amount: | 29950
| OBJECTIVE: |  | Cut and Cap Casing | [8 empty] | Start Date: | 2016-03-07
| Formation: |  | Perforations (mKB) |  |  | Perforations (mKB) |  |  | Perforations (mKB) |  |  | End Date: | 2016-09-26
| Arnica (abandoned) |  | 3630 | to | 3642 |  | to |  |  | to |  | Rig Contractor / No.: | Rigless
| Nahanni |  | 3128.8 | to | 3449.7 |  | to |  |  | to |  | Csg. Dia (mm): | 177.8 | Set At (mKB): | 3757
|  |  |  | to |  |  | to |  |  | to |  | Liner O.D. (mm): |  | Top At (mKB):
|  |  |  | to |  |  | to |  |  | to |  | Liner Bot. (mKB): |  | PBTD (mKB): | 434.4
|  |  |  | to |  |  | to |  |  | to |  | Tbg. O.D. (mm): |  | Landed (mKB):
|  |  |  | to |  |  | to |  |  | to |  | Anchor (mm): |  | Set At (mKB):
|  | BOP P-Test Date: |  |  | Satisfactory: |  |  |  | Function Test: |  |  |  | Safety Meeting: | Yes
| 24 Hour Summary |  |  | Fly to location, perform soil gas migration test, return to base
| Next 24 Hour Forecast |  |  | Job complete
| OPERATION DETAILS |  |  | SCV (kPa) |  |  | SICP (kPa) |  |  | SITP (kPa) |  |  | DAILY COST SUMMARY
[12 empty] | Description | Account | Number | Amount
[12 empty] | Contract Supervision | 70021 | 1 | 1287
[12 empty] | Air Transportation | 70002 | 1 | 800
[12 empty] | Daily Cost: |  |  | 2087
[12 empty] | Previous Cost: |  |  | 22744.08
[12 empty] | Cum. Cost: |  |  | 24831.08
| Wellbore Vol (m³) |  | Res Fluids | Previous | Daily | To Date | Flaring (e³m³) |  | Previous | Daily | To Date | Load Fluids | Water (m³) | Oil (m³) | Gas (e³m³)
| Tubing: |  | Gas (e³m³) | 0 |  | 0 | Total Gas |  | 0 | 0 | 0 | To Location | 0 | 0 | 0
| Annulus: |  | Oil (m³) | 0 |  | 0 | - Dilution Gas |  | 0 | 0 | 0 | From Location | 0 | 0 | 0
| Btm - Perf: |  | Water (m³) | 0 |  | 0 | - N₂ & CO₂ |  | 0 | 0 | 0 | On Location | 0 | 0 | 0
|  |  | Swab Hrs | 0 |  | 0 | Raw Gas |  | 0 | 0 | 0 | Load To Recover | 0 | 0 | 0
| Total: | 0 | Flow Hrs | 0 |  | 0 | No Flaring To Report |  |  |  |  | Recovery Over Load | 0 | 0 | 0
|  | Tour Hours. |  |  | Personnel on Location |  |  |  | Equipment on Location: |  |  | Weather Conditions: | Morning Overcast 7c
| Daily: | 14 |  | Rig: |  |  | Jet Ranger Helicopter |  |  |  |  | Road Conditions:
| Cumulative: |  | 14 | Service: | 1
| Downtime: | 0 |  | Apache: | 1
| Cum. Downtime: |  | 0 | Total: | 2
| NPT: | 0Hrs; Cost: $0 |  | Frac | No Frac to Report
DAILY OPERATIONS NWT Abandonment Report
Engineer: Don Jones Phone:
Report To: Richard Bean Phone: (403) 303-1929
WSS 1: Brian Dickson Phone: (780) 518-5800
WSS 2: Phone:
08:00 hrs. - Held documented safety meeting with all personnel, reviewed helicopter loading / off-loading procedures and job scope for the day.
09:00 hrs. - Arrived on location, performed soil gas migration test around the wellhead. Bored 14 holes, 5cm x 50 cm, at 30 cm, 2 m, 4 m and 6 m meters from the wellhead in four compass directions of North, East, South and West.
- Using a GIG Instrumentation Inc. four (4) head monitor c/w pump attachment, checked all 14 holes for LEL's and H₂S with none found. Recorded data and took pictures, from well center, pointing North, East, South and West.
10:00 hrs. - End of tour, job completed, helicopter to next location.
Pictures added to report, soil gas migration attached to e-mail.

## Cost-Vendor
Cost-Vendor
| Prepared By: Apache Canada Ltd. "Sense of Urgency" | [7 empty] | Vendor Report
UWI: 300/A-55-6030-12345/02 Well Name: APACHE AMOCO A-4 POINTED MOUNTAIN A-55Licence #: N911 AFE No.: 20-14-0478
| AFE Estimate $29,950 |  |  | Start Date Monday Mar 07, 2016
| Total Actual $24,831 |  |  | End Date Monday Sep 26, 2016
| Difference -$5,119 |  |  | Percent AFE 82.908%
| Date | Day | Vendor | Field Ticket | Account Description | Account | Amount | Comment | Recurring | CommentID
| 2016-03-07 | 1 | 3-D Line Locating | RPV 000497 | Contract Labor & Services | 70017 | 540 | Line locating | FALSE | ID53343-1-2-7568
| 2016-03-10 | 2 | JAZA Oilfield Consulting Ltd. | APA-381 | Contract Supervision | 70021 | 1725 | Supervision - Brian Dickson | FALSE | ID53343-2-2-7568
| 2016-03-10 | 2 | Scott Safety Services | 83166 | Safety Case | 70529 | 845 | Mecdic & MTC | FALSE | ID28958-2-3-7568
| 2016-03-10 | 2 | FMC Technologies | 608342 | Contract Labor & Services | 70017 | 2695.5 | Crew to assist with cut and cap operations | FALSE | ID77474-2-4-7568
| 2016-03-10 | 2 | Bert Baxter Transport | 29237 | Trucking and Hauling | 70074 | 3500 | Picker to assist with cut and cap operations, load wellhead | FALSE | ID76073-2-5-7568
| 2016-03-10 | 2 | Troyer Ventures | FN121136 | Contract Labor & Services | 70017 | 1520 | Steamer to assist with cut and cap operations | FALSE | ID70905-2-6-7568
| 2016-03-10 | 2 | Acho camp & catering | 9999 | Camp | 70005 | 3105 | Rooms and meals for crew | FALSE | ID53345-2-7-7568
| 2016-03-10 | 2 | Dushay Welding Ltd. | 17057 | Contract Labor & Services | 70017 | 3632.4 | Welder to cut and cap casing strings | FALSE | ID53346-2-8-7568
| 2016-03-10 | 2 | Beaver Enterprises | 50407 | Contract Labor & Services | 70017 | 4216 | Hoe and CAT to assist with cut and cap operations | FALSE | ID53346-2-9-7568
| 2016-03-10 | 2 | Total Oilfield Rentals | FN99529894 | Trucking and Hauling | 70074 | 485.1 | Haul wellheads from Ft. Nelson to Stream-Flo, Ft. St. John | FALSE | ID53347-2-10-7568
| 2016-03-10 | 2 | KETEK Group | RI-125558 | Equipment Rental | 70031 | 480.08 | Rentals | FALSE | ID53347-2-11-7568
| 2016-09-26 | 3 | JAZA Oilfield Consulting Ltd. | APA-389 | Contract Supervision | 70021 | 1287 | Supervision for Sept. 25 & 26 | FALSE | ID53343-3-2-7568
| 2016-09-26 | 3 | Qwest Helicopters | 41670 | Air Transportation | 70002 | 800 | Helicopter to fly to location | FALSE | ID77474-3-3-7568